## Version 0.2.0
VERSION 0.2.0: THE QUALITY OF LIFE UPDATE
No. | Description | Done? | Comments | LEGEND
1 | Update code to be PEP 8 compliant | YES |  | PTFU | Pushed to a Future Update
2 | Update functions' docstrings to be PEP 257 compliant | YES
3 | Implement Sredictio GUI | PTFU | Pushed to Version 0.3.0
4 | Complete Sredictio Field Tests (SFTs) | YES | To update Main.py after analysis on SFTs' results
5 | Implement Training Data Updater | YES
6 | Update Training Data | YES
7 | Make running Sredictio easier | YES | To complete update on Main.py first before confirming.
8 | Update Main.py's OHLCV parsing algorithm | YES
9 | Update Model and Hyperparameters.db for better training/testing | YES

## Version 0.3.0
VERSION 0.3.0: THE GUI UPDATE
No. | Description | Done? | Comments | LEGEND
1 | Implement a working GUI for Sredictio | NO | Will fix Issue #6 first | PTFU | Pushed to a Future Update
2 | Convert all Main.py code to Functions | YES | Waiting to implement them to the GUI functions
3 | Implement Sredictio Updater program | YES
4 | Fix TradingEnv.py's rendering method | YES
5 | Resolve Issue #6: Model Prediction is too Consistent | NO | Investigation of TradingEnv.py's observation state is underway; may take some time.
5a | Fix observation state | NO | Bug in observation state is unclear; will need time
5b | Regenerate Hyperparams.db | NO
5c | Retrain the A2C model | NO
6 | Fix bugs | PENDING | Fixing Issue #6.